## What to do
WHAT TO DO ? | BEFORE | DURING | AFTER | STATUS | DONE
General Orgaisation
Define a date in collaboration with the official provider working for Swiss Taekwondo | D-365 |  |  | 0% | 0
Book a venue and all the needed material from the municipality (tables, chairs, bins, electricity, ...) | D-365 |  |  | 0% | 0
Sponsoring and Partnership Request | D-365
Depending of the Kanton, request specific autorisation for event organization | D-365
Update the outline with all the required information to be communicated to clubs and send it to EB and Technical Delegate for approbal | D-180 |  |  | 0% | 0
Book a Doctor specialized in Trauma | D-180 |  |  | 0% | 0
Book an Ambulance with Samaritains | D-180 |  |  | 0% | 0
Once the competition is created in the OVR website, send out the outline to the clubs | D-180 |  |  | 0% | 0
Design and order the rewards | D-180 |  |  | 0% | 0
Plan the specific required materials | D-90 |  |  | 0% | 0
Plan the number of volunteers per position | D-90 |  |  | 0% | 0
Plan the cateering for officials, volunteers, participants and public | D-90 |  |  | 0% | 0
Send invitation to the municipalty | D-90 |  |  | 0% | 0
Book accomodation for Officials and Referees | D-30 |  |  | 0% | 0
Flags (Swiss, South Korea, Club) | D-3 | D-1 |  | 0% | 0
Swiss National Anthem | D-3 | D-1 |  | 0% | 0
IT - Sound: computers, printers, cables, microphones, batteries, etc. | D-3 | D-1 |  | 0% | 0
Plan the distribution of volunteers | D-3 | D-1 |  | 0% | 0
Installation of the Venue | D-1 | D |  | 0% | 0
Office equipment: Staplers, pens, markers, sheets of paper, string, tacks, scissors, scotch tape, etc. | D-1 | D |  | 0% | 0
Assigning and briefing volunteers for their posts | D-1 | D |  | 0% | 0
Make final adjustments to accommodate last-minute additions and absences | D-1 | D |  | 0% | 0
Awards ceremony | D-1 | D |  | 0% | 0
Indoor-Outdoor Signage | D-1 | D |  | 0% | 0
Site decoration Banners, Matts,… | D-1 | D |  | 0% | 0
Communication (Facebook - Instagram, sending photos and report to referent) | D-60 | D | D+3 | 0% | 0
Venue Cleaning |  | D | D+1 | 0% | 0
Matts and other materials to return |  | D | D+1 | 0% | 0
Send photo and information to Swiss Taekwondo News (swisstkd.news@gmail.com) for publication |  | D | D+3 | 0% | 0
Send proof of Payment for referees to Technical Delegate for Swiss Taekwondo Reimboursment |  | D | D+10 | 0% | 0